## Readout HW Status Update
Last update: | 2015-03-27 |  | Phase
Board | Module | Design | Fabrication | Assembly | Calibration/Test | Ship to KEK | Start Assembly at KEK
SCROD revA5 | 001~025 |  | 2015-02-20 | 2015-03-06 | 2015-04-10 |  |  | Test using the complete setup
SCROD revA5 | 026~144 |  |  | 2015-05-15 |  |  |  | May or may not need to test all remaining scrods separately
Motherboard RevC | 001~010 | 2015-03-27 | 2015-04-10 | 2015-04-24 | 2015-05-01 | 2015-05-08 | 2015-05-29 | Chris to Hand carry 2-3 MBs and install at KEK for taking data
Motherboard RevC | 011~144 | 2015-04-10: 2015-05-15; 2015-04-24: 2015-05-29; 2015-05-01: 2015-06-28
Motherboard RevC | 011~060 | 2015-05-08: 2015-06-12; 2015-05-29: 2015-06-19
RHIC RevC | 001~010 | 2015-03-27 | 2015-04-10 | 2015-04-24 | 2015-05-01 | 2015-05-08 | 2015-05-29 | Get paperwork in advance for customs
RHIC RevC | 011~144 | 2015-04-10: 2015-05-15; 2015-04-24: 2015-05-29; 2015-05-01: 2015-06-28
RHIC RevC | 011~060 | 2015-05-08: 2015-06-12; 2015-05-29: 2015-06-19
Daughtercard RevC | 0001~0100 | 2015-03-27 | 2015-04-10 | 2015-04-24 | 2015-05-01 | 2015-05-08 | 2015-05-29
Daughtercard RevC | 101~550
Daughtercard RevC | 0100~0490
Calibration and Test review meeting: |  | 2015-03-27: 2015-03-20; 2015-04-10: Done with production testing review- plan as we go. updated the schedule and test procedures
1550 is including %15 spares
make 150 bare boards for RHIC and MB, but not assemble them
notes for the 3/27/2015 meeting
Final review Monday 3/30/2015 at 8am HST
once we verify that digital parts work we can put in the order
Get fab quotes
Get this excel sheet updated and posted after the design review