## Sheet1
Hodoscope Daughter Card (DC)
Task | Status | Person in Charge | Target Deadline
Revise BMD_REVB board (Layout and schematic) | Done | Gary | N/A
Update mRich_Hodoscope_DC UCF | DONE | Nathan | 2018-05-17
Fabrication | Done | Gary | N/A
Prototype Population | In Progress | William, Nathan, Julien | 2018-05-16
Prototype Test 1: DC-Scrod+Rj45 smoke test | DONE. | Nathan | 2018-05-17
Prototype Test 2: DC-Scrod+Rj45 Functionality test | Not started. Dependencies: population up to one DC channel. Prototype Test 1 Successful | Isar | 2018-05-17
Full Operation Population | Not started. Dependencies: Successful Prototype. Inventory fully stocked | William | 2018-05-25
Transition Board
Task | Status | Person in Charge | Target Deadline
Layout of Leftside | Done | Gary | N/A
Fabrication of Leftside | In Progress: Quote Request | Julien/Tommy | 2018-05-21
Update UCF | In Progress | Tommy | ??????????????
Carrier Board
Task | Status | Person in Charge | Target Deadline
Prototype Layout: 4-layer | Done | Julien/Emily | N/A
Prototype Fabrication | Done: Arrived | Julien/Emily | N/A
Order Stencil | In Progress: send gerber file | Julien/Jose | 2018-05-21
Prototype Population | Not started. Dependencies: Order Stencil | Julien | ??????????????
Prototype Testing | Not started. Dependencies: Order Stencil | Julien | ??????????????
V2 Layout | Done (pending approval) | Julien/Emily | N/A
V2 Fabrication | Not started. Dependencies: Prototpye Testing | Julien | ??????????????
TX_DC
Task | Status | Person in Charge | Target Deadline
Layout | Done
FW? | ?? | ??
Fabrication | In Progress | Julien, Tommy (in contact with Manufacturer, PCB Universe) | 5/20/2018 (5-day turn around)
Population | Not Started. Dependencies: Fabrication | (Tentative) Emily | ??????????????
RJ-45 Board
Task | Status | Person in Charge | Target Deadline
Fabrication | Done | Khanh | N/A
Population | Done | Khanh | N/A
Update UCF | DONE | Nathan | 2018-05-09
Firmware: Serial communication | In Progress | Isar
Prototype Test 1: DC-Scrod+Rj45 smoke test | Not started. Dependencies: prototype population up to one DC channel | Isar | 2018-05-18
Prototype Test 2: DC-Scrod+Rj45 Functionality test | Not started. Dependencies: population up to one DC channel. Prototype Test 1 Successful | Isar | 2018-05-18
Parts Kit
Task | Status | Person in Charge | Target Deadline
BOM/schematic Printing | DONE | Nathan | 2018-05-21
Components Audit: Find Substitutes for Missing Parts | Done: BOM w/ Inventory compiled on Drive Spreadsheet | Nathan | 2018-05-18
Parts Kit Box Organization | Done | Nathan | 2018-05-20
Documentation
Task | Status | Person in Charge | Target Deadline
Hodoscope 3D Model | In Progress | Tommy | 2018-05-16
Transition 3D Model | Done | Tommy | N/A
Carrier 3D Model | Done | Tommy | N/A
TX_DC 3D Model | Done | Tommy | N/A
Mechanical Structure CAD and Integrated mRich Model | In Progress. Dependencies: Other 3D models | Marrissa | ??????????????
Note on A50: Order remaining missing parts -Nathan Park