## Nu react test prep
mTC scheduling -- essential milestones
Schedule to NIST reactor neutrino run - projected January 2014 | 2013-09-30 | 2013-10-07 | 2013-10-14 | 2013-10-21 | 2013-10-28 | 2013-11-04 | 2013-11-11 | 2013-11-18 | 2013-11-25 | 2013-12-02 | 2013-12-09 | 2013-12-16 | 2013-12-23 | 2013-12-30 | 2014-01-06 | 2014-01-14 | 2014-01-21
Item
mTC Production Runs and assembly
SCROD validation | 2013-09-30: LM/JM/SL; 2013-10-07: LM/JM/SL; 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL
Interconnect validation | 2013-09-30: LM/JM/SL; 2013-10-07: LM/JM/SL; 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL
Carrier02 validation | 2013-09-30: LM/JM/SL; 2013-10-07: LM/JM/SL; 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL
Carrier13 validation | 2013-09-30: LM/JM/SL; 2013-10-07: LM/JM/SL; 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL
Whole Boardstack assembly | 2013-09-30: LM/JM/SL; 2013-10-07: LM/JM/SL; 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL
Boardstack repair? | bar: 2013-09-30 to 2013-11-11
mTC-specific Firmware | bar: 2013-09-30 to 2013-10-14
Evaluation | bar: 2013-09-30 to 2013-10-21
CAJIPC
Firmware | 2013-09-30: SN/LM; 2013-10-07: SN; 2013-10-14: SN; 2013-10-21: SN
Evaluation | bar: 2013-09-30 to 2013-10-21
Power/Thermal
Estimation and conceptual design | 2013-09-30: DONE
Procurement - cooling plates | 2013-09-30: DONE
Procurement - external freezer | bar: 2013-09-30 to 2013-10-07
Mechanical design, manufacturing, assembly | bar: 2013-09-30 to 2013-10-07
Thermal Testing | bar: 2013-10-07 to 2013-10-28
mTC electronic assembly and testing
Full Assembly | 2013-09-30: JM/SL/MR; 2013-10-07: JM/SL/MR; 2013-10-14: JM/SL/MR; 2013-10-21: JM/SL/MR; 2013-10-28: JM/SL/MR; 2013-11-04: JM/SL/MR; 2013-11-11: JM/SL/MR; 2013-11-18: JM/SL/MR
In-Lab testing: Gammas | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | mTC ready for data-taking
In-Lab testing: Neutron | 2013-10-14: LM/JM/SL; 2013-10-21: LM/JM/SL; 2013-10-28: LM/JM/SL; 2013-11-04: LM/JM/SL; 2013-11-11: LM/JM/SL; 2013-11-18: LM/JM/SL; 2013-11-25: LM/JM/SL; 2013-12-02: LM/JM/SL; 2013-12-09: LM/JM/SL; 2013-12-16: mTC ready for data-taking
In-Lab testing: Compton | Compton procurement? |  | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | LM/JM/SL | mTC ready for data-taking
cPCI_DSP
Trigger Firmware | 2013-09-30: SN/LM; 2013-10-07: SN/LM; 2013-10-14: SN/LM; 2013-10-21: SN/LM
Evaluation | bar: 2013-09-30 to 2013-12-09
calibration board | bar: 2013-09-30 to 2013-12-09
Design | bar: 2013-09-30 to 2013-10-21
Manufacturing/assembly | bar: 2013-10-28 to 2013-11-11
test | 2013-11-18: LM/LR; 2013-11-25: LM/LR
Installation/calibration | 2013-12-02: LM/JM/LR; 2013-12-09: LM/JM/LR
NIST reactor test
shipment | bar: 2013-12-16 to 2013-12-23
In loco assembly | bar: 2013-12-30 to 2014-01-06
Reactor test | 2014-01-21: Ready for Reactor Test
TENTATIVE ASSIGNMENTS of TASKS
LM= Luca Macchiarulo
SN= Serge Negrassov
JM= Josh Murillo
MR= Mark Rosen
SL= Slava Li
LR= Lisa Ritter