## Sheet1
ID Lab Scheduling Overview
|  | 2010-01-04 | 2009 |  |  |  | 2010
|  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept
| Project with Deliverables | Subtask | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | xFEL beamline | beamline sims | bar: Dec 4
Measurements | bar: Dec 4 to Jan 1
Preliminary CDR detect | bar: Dec 4 to Jan 1
Preliminary CDR ASIC | bar: Jan 1
Preliminary TDR Readout | bar: Jan 1
2 | Nagoya laser scan (SL-10) | Module design | bar: Dec 1 to Dec 4
firmware development | bar: Jan 1 to Feb 4
software development | bar: Jan 1 to Feb 4
Complete piLas stand | bar: Jan 1 to Jan 4
BLAB3 ASICs (12) | bar: Jan 3
Modules assembly | bar: Jan 4 to Feb 1
Modules evaluate | bar: Feb 1 to Feb 4
Ship modules (6x) | bar: Feb 4
3 | KEK (Photonis) delivery | Module design | bar: Dec 4 to Jan 1
firmware (same as 2) | bar: Jan 1 to Feb 4
software (same as 2) | bar: Jan 1 to Feb 4
BLAB3 ASICs (28) | bar: Jan 3
Modules assembly | bar: Jan 4 to Feb 1
Modules evaluate | bar: Feb 1 to Feb 4
Ship modules (7x) | bar: Feb 4
Coming Deadlines
| today | MPPC laser test | bar: Dec 4 to Jan 1
| Jan 25, 26 (Korea) | Belle II Trg/DAQ | bar: Jan 4
| Feb. 1st, May 10th | LAPD next ASIC (spec, x) | bar: Feb 1; May 1
| Feb. 3rd | xTOP TDR draft | bar: Feb 1
| Jan. 5th | ADR LoI | bar: Jan 1
| Feb. 1st | ADR Proposal | bar: Feb 1
| Jan. 18th | B2Note precision timing | bar: Jan 3
| Jan. 25th | B2Note rad hard testing | bar: Jan 4
| Feb. 15 | LAPD TDR | bar: Feb 3