## Sheet1
Year 1 Development Schedule for Integrated x-ray Readout/DAQ
29-dec-09//GSV
|  |  | Sept |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sept
| Task | Subtask | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1 | 350ps bunch separation demonstrator | optical comp acquisition | bar: Sept 1 to Oct 2
bench commission | bar: Oct 2 to Oct 4
acquire photodetectors | bar: Sept 2 to Oct 4
CDR | bar: Sept 4
simple DAQ USB (exist) | bar: Nov 1 to Nov 3
PD/RO interface board | bar: Oct 2 to Nov 3
Specs verification/TDR | bar: Nov 4 to Dec 1
commission | bar: Dec 2 to Dec 3
Measurements | bar: Dec 4 to Jan 1
2 | Fast DAQ system | XMC readout design | bar: Sept 1 to Oct 2
cPCI crate/CPU acq. | bar: Oct 1 to Oct 4
CDR | bar: Sept 4; Dec 1
Fast link fabrication | bar: Oct 3 to Nov 4
firmware development | bar: Dec 1 to Feb 4
software development | bar: Jan 1 to May 2
Readiness Review | bar: Feb 3; May 2
integration/test | bar: Feb 4 to April 4; May 3
3 | ps2 ASIC | Specs confirm | bar: Sept 1 to Sept 3; May 3
Preliminary design | bar: Sept 4 to Oct 4; May 3
CDR | bar: Nov 1; Dec 1; May 3
Detailed simulations | bar: Nov 2 to Dec 1; May 3
Layout | bar: Dec 2 to Dec 3; May 3
Design Review | bar: Dec 4; May 3
MOSIS fabrication | bar: Jan 1 to March 2; May 3
Eval board fab + test | bar: March 1 to April 4; May 3
Integrated module design | bar: Jan 1 to May 2
Integrated module fab | bar: May 3 to July 2
Integration + operation | bar: July 3 to Sept 3
first beam | bar: Sept 4
4 | Custom Sensor 1 | Specs confirm | bar: Sept 1 to Oct 4
design + simulation | bar: Sept 3 to Jan 1
prototype eval | bar: Dec 2 to Jan 2
CDR | bar: Jan 3
detailed simulations | bar: Jan 4 to Sept 3
Design Review | bar: Sept 4
fabrication